## Dashboard
Go Live date shown under status, "blank" if no dates | Number of TPs in each State | Count of TPs where a Go Live date has been proposed to the TP for acceptance | Count of TPs with a planned Go Live date accpted by the TP
Row Labels | Sum of Helper | Count of Go Live Proposed (Date) | Count of Go Live Planned (Date) | Overall TP Status | Description
1 | 13 |  | 19 | De-Scoped | Removed from the scope of the project
De-scoped | 2 |  | 1 | Await Contact Details | IBM Awaiting contact details from PF
04.12.2017 | 1 |  | 1 | Not Started | IBM have not contacted the TP yet
(blank) | 1 |  |  | Waiting on TP Coms1 | 1st Contact Letter sent by IBM
Live | 11 |  | 18 | Waiting on TP Coms2 | 2nd Contact Letter sent by IBM
04.12.2017 | 3 |  | 8 | Waiting on TP Coms3 | 3rd Contact Letter sent by IBM
18.12.2017 | 1 |  | 1 | TP Coms Except | Coms Exception, PF to follow up with TP, no response to IBM
2018-01-15 | 4 |  | 6 | On Hold | TP on hold for some reason - See comments
2017-12-04 | 2 |  | 2 | Discovery | IBM in discussions with TP to understand requirements
2018-01-29 | 1 |  | 1 | TP Setup | IBM have set up the TP in the Test System
2.1 | 47 | 180 | 55 | System Testing | PF/IBM testing
Live | 6 | 15 | 15 | E2E Test Slot Proposed | CDS team have proposed a slot for E2E testing and are awaiting confirmation
2018-02-12 | 6 | 15 | 15 | E2E Test Slot Agreed | TP has agreed a slot for E2E testing
TP Coms Except | 1 | 5 |  | E2E Testing | TP has confirmed readiness to test and window has been confirmed
(blank) | 1 | 5 |  | Production Readiness | Testing Completed Ready to Migrate
Waiting on TP Coms1 | 2 | 10 |  | E2E Test Failed | Test Failed Change Required
(blank) | 2 | 10 |  | Migration Booked | Migration Data Booked with TP and PF
Waiting on TP Coms2 | 12 | 39 |  | Live | Migration Complete
(blank) | 12 | 39 |  | Non-EDI Process | PF will (temporarily) move to Non-EDI process
Waiting on TP Coms3 | 3 | 5 |  | OB10/Tungsten | Process as OB10/Tungsten as the TP
(blank) | 3 | 5 |  | BizTalk | TPs that will move to BizTalk
E2E Testing | 13 | 52 | 7
(blank) | 12 | 45
2018-02-19 | 1 | 7 | 7
E2E Test Slot Agreed | 2 | 9
(blank) | 2 | 9
Migration Booked | 4 | 33 | 33
(blank) | 0
2018-02-14 | 3 | 25 | 25
2018-02-20 | 1 | 8 | 8
Production Readiness | 4 | 12
(blank) | 4 | 12
2.2 | 45 | 154 | 18
De-scoped | 1 | 1
(blank) | 1 | 1
Live | 1 | 1 | 1
2018-02-12 | 1 | 1 | 1
TP Coms Except | 9 | 26
(blank) | 9 | 26
TP Setup | 3 | 7
(blank) | 3 | 7
Waiting on TP Coms1 | 8 | 42
(blank) | 8 | 42
Waiting on TP Coms2 | 5 | 18
(blank) | 5 | 18
Waiting on TP Coms3 | 1 | 3
(blank) | 1 | 3
E2E Testing | 8 | 19
(blank) | 8 | 19
E2E Test Slot Agreed | 2 | 15
(blank) | 2 | 15
Migration Booked | 4 | 15 | 15
2018-02-19 | 3 | 10 | 10
2018-02-28 | 1 | 5 | 5
Production Readiness | 2 | 5 | 2
(blank) | 1 | 3
2018-02-19 | 1 | 2 | 2
E2E Test Slot Proposed | 1 | 2
(blank) | 1 | 2
2.3 | 33 | 32
Await Contact Details | 2 | 3
(blank) | 2 | 3
BizTalk | 5
(blank) | 5
De-scoped | 8
(blank) | 8
TP Coms Except | 5 | 8
(blank) | 5 | 8
TP Setup | 1 | 3
(blank) | 1 | 3
Waiting on TP Coms1 | 3 | 7
(blank) | 3 | 7
OB10/Tungsten | 8 | 8
(blank) | 8 | 8
E2E Test Slot Proposed | 1 | 3
(blank) | 1 | 3
3 | 32 | 16
BizTalk | 1
(blank) | 1
De-scoped | 5
(blank) | 5
TP Coms Except | 1
(blank) | 1
TP Setup | 9 | 10
(blank) | 9 | 10
Waiting on TP Coms1 | 1
(blank) | 1
On Hold | 5 | 6
(blank) | 5 | 6
Waiting on TP Coms2 | 2
(blank) | 2
Waiting on TP Coms3 | 4
(blank) | 4
E2E Testing | 3
(blank) | 3
Discovery | 1
(blank) | 1
4 | 2
TP Setup | 0
(blank) | 0
E2E Testing | 2
(blank) | 2
(blank)
(blank)
(blank)
Legend (color):
(blank)
(blank)
Grand Total | 172 | 382 | 92

## SteeringBoard
Total Number of Trading Partners | 172 | Live | 18
Trading partners Descoped | 24 | Remaining to Go Live | 130
Remaining Trading Partners | 148
R1.0 Trading Partners | 11
Live | 11
R2.1 Trading Partners [Week 12th Feb] | 47 | R2.2 Trading Partners [Week 19th Feb] | 44 | R2.3 Trading Partners [Week 26th Feb] | 25
Setup | 0 | Setup | 3 | Setup | 1
Awaiting Details/OB10 | 0 | Awaiting Details/OB10 | 0 | Awaiting Details/OB10 | 10
Awaiting Response | 17 | Awaiting Response | 15 | Awaiting Response | 3
On Hold | 0 | On Hold | 0 | On Hold | 0
In Test | 15 | In Test | 10 | In Test | 0
Production Readiness | 4 | Production Readiness | 2 | Production Readiness | 0
Migration Agreed [Subject to] | 0 | Migration Agreed [Subject to] | 0 | Migration Agreed [Subject to] | 0
Migration Booked | 4 | Migration Booked | 4 | Migration Booked | 0
Move to BizTalk | 0 | Move to BizTalk | 0 | Move to BizTalk | 5
In Exception | 1 | In Exception | 9 | In Exception | 5
Live | 6 | Live | 1 | Live | 0
R3.0 Trading Partners [Week 12th March] | 27
Setup | 10 | Move to "in Test" Velocity | 5.1667 | Per Day
Awaiting Details/OB10 | 0 | Rolling Week Move to "in Test"
Awaiting Response | 7 | 12th Feb | 0
On Hold | 5 | 9th Feb | 3
In Test | 3 | 8th Feb | 7
Test Slot/Migration Agreed [Subject to] | 0 | 7th Feb | 6
Migration Booked | 0 | 6th Feb | 8
Move to BizTalk | 1
In Exception | 1
Live | 0
[6 empty] | Rolling Week Move to "in Test" | Moved | Days Tracking
[6 empty] | 12th Feb | 0 | 1 | 6
[6 empty] | 9th Feb | 3 | 1
[6 empty] | 8th Feb | 7 | 1
[6 empty] | 7th Feb | 6 | 1
[6 empty] | 6th Feb | 8 | 1
[6 empty] | 5th Feb | 7 | 1
[10 empty] | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M | T | W | T | F | S | S | M
[9 empty] | MinVel | 2018-02-12 | 2018-02-13 | 2018-02-14 | 2018-02-15 | 2018-02-16 | 2018-02-17 | 2018-02-18 | 2018-02-19 | 2018-02-20 | 2018-02-21 | 2018-02-22 | 2018-02-23 | 2018-02-24 | 2018-02-25 | 2018-02-26 | 2018-02-27 | 2018-02-28 | 2018-03-01 | 2018-03-02 | 2018-03-03 | 2018-03-04 | 2018-03-05 | 2018-03-06 | 2018-03-07 | 2018-03-08 | 2018-03-09 | 2018-03-10 | 2018-03-11 | 2018-03-12 | 2018-03-13 | 2018-03-14 | 2018-03-15 | 2018-03-16 | 2018-03-17 | 2018-03-18 | 2018-03-19 | 2018-03-20 | 2018-03-21 | 2018-03-22 | 2018-03-23 | 2018-03-24 | 2018-03-25 | 2018-03-26 | 2018-03-27 | 2018-03-28 | 2018-03-29 | 2018-03-30 | 2018-03-31 | 2018-04-01 | 2018-04-02 | 2018-04-03 | 2018-04-04 | 2018-04-05 | 2018-04-06 | 2018-04-07 | 2018-04-08 | 2018-04-09 | 2018-04-10 | 2018-04-11 | 2018-04-12 | 2018-04-13 | 2018-04-14 | 2018-04-15 | 2018-04-16 | 2018-04-17 | 2018-04-18 | 2018-04-19 | 2018-04-20 | 2018-04-21 | 2018-04-22 | 2018-04-23 | 2018-04-24 | 2018-04-25 | 2018-04-26 | 2018-04-27 | 2018-04-28 | 2018-04-29 | 2018-04-30
[7 empty] | March | 132 | 4.4 | M: 4.4; T: 4.4; W: 4.4; T: 4.4; F: 4.4; M: 4.4; T: 4.4; W: 4.4; T: 4.4; F: 4.4; M: 4.4; T: 4.4; W: 4.4; T: 4.4; F: 4.4; M: 4.4; T: 4.4; W: 4.4; T: 4.4; F: 4.4; M: 4.4; T: 4.4; W: 4.4; T: 4.4; F: 4.4; M: 4.4; T: 4.4; W: 4.4; T: 4.4; F: 4.4
[7 empty] | April | 130 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6 |  |  | 2.6 | 2.6 | 2.6 | 2.6 | 2.6

## Dashboard_12Feb
Row Labels | Sum of Helper | Overall TP Status | Description
1 | 13 | De-Scoped | Removed from the scope of the project
De-scoped | 2 | Await Contact Details | IBM Awaiting contact details from PF
Live | 11 | Not Started | IBM have not contacted the TP yet
2.1 | 47 | Waiting on TP Coms1 | 1st Contact Letter sent by IBM
E2E Test Slot Agreed | 2 | Waiting on TP Coms2 | 2nd Contact Letter sent by IBM
E2E Testing | 13 | Waiting on TP Coms3 | 3rd Contact Letter sent by IBM
Live | 6 | TP Coms Except | Coms Exception, PF to follow up with TP, no response to IBM
Migration Booked | 4 | On Hold | TP on hold for some reason - See comments
Production Readiness | 4 | Discovery | IBM in discussions with TP to understand requirements
TP Coms Except | 1 | TP Setup | IBM have set up the TP in the Test System
Waiting on TP Coms1 | 2 | System Testing | PF/IBM testing
Waiting on TP Coms2 | 12 | E2E Test Slot Proposed | CDS team have proposed a slot for E2E testing and are awaiting confirmation
Waiting on TP Coms3 | 3 | E2E Test Slot Agreed | TP has agreed a slot for E2E testing
2.2 | 45 | E2E Testing | TP has confirmed readiness to test and window has been confirmed
De-scoped | 1 | Production Readiness | Testing Completed Ready to Migrate
E2E Test Slot Agreed | 2 | E2E Test Failed | Test Failed Change Required
E2E Testing | 8 | Migration Booked | Migration Data Booked with TP and PF
Live | 1 | Live | Migration Complete
Migration Booked | 4 | Non-EDI Process | PF will (temporarily) move to Non-EDI process
Production Readiness | 2 | OB10/Tungsten | Process as OB10/Tungsten as the TP
TP Coms Except | 9 | BizTalk | TPs that will move to BizTalk
TP Setup | 3
Waiting on TP Coms1 | 8
Waiting on TP Coms2 | 5
Waiting on TP Coms3 | 1
E2E Test Slot Proposed | 1
2.3 | 33
Await Contact Details | 2
BizTalk | 5
De-scoped | 8
OB10/Tungsten | 8
TP Coms Except | 5
TP Setup | 1
Waiting on TP Coms1 | 3
E2E Test Slot Proposed | 1
3 | 32
BizTalk | 1
De-scoped | 5
Discovery | 1
E2E Testing | 3
On Hold | 5
TP Coms Except | 1
TP Setup | 9
Waiting on TP Coms1 | 1
Waiting on TP Coms2 | 2
Waiting on TP Coms3 | 4
4 | 2
E2E Testing | 2
TP Setup | 0
Legend (color):
(blank)
(blank)
(blank)
Grand Total | 172

## TP Summary
Release Lvl | Region | TP Company Name | TP's EDI code | Helper | TP Qualifier | PF's new EDI Codes | PF's new EDI Qualifier | PF 's old EDI Codes | PF's old EDI Qualifier | REIMS /TP a/c number | REIMS Interchange | Message Type | Direction To/From Client | SFTP / MQ Protocol | Message Format | Version | Envelope Variant | Comms Type | TP's Provider | X.400 address (if applicable) | Contact Name/Email address | Telephone | CDS Notes | CDS Info | Comments | Action's Owner | Relationship Status | TP Overall Status | Specs Received (Date) | Test Data Received (Date) | MRS created (Date) | MRS Signed off (Date) | Maps approved for System Test (Date) | IBM Mapname | Map Type | REIMS Base Map To Use | Map Loaded (Date) | TP Setup (Date) | System Test (Date) | System Test Signed off (Date) | End to End Test Planned (Date) | End to End Test Signed off (Date) | Go Live Proposed (Date) | Go Live Planned (Date) | Moved To production (Date) | Go Live (Date)
2.3 | EU | 3M UNITED KINGDOM PLC | 5013546030160 | 1 | UK21 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | 3M-UK | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | IBM |  | cbuckley@tp1.com |  |  | TP never respond | 7.2.18 comms escalated to client. 21.11.2014 Email to PF: we have no reply from this TP. 16.11.2017 Email to TP. sent out Email to TP which Andre have prepared - last request. 13.11.2017 Email to TP, 4th Followup sent, 06.11.2017: 3rd Remainder email sent to TP 31.10.2017: Email to TP 2nd Followup sent23.10.2017: Email to TP Followup sent 17.10.2017: Introduction email to TP : We represent IBM EMEA Community Development Services working with Premier Farnellon their Trading Partner Implementation project, in which Premier Farnell are committed to simplifying and improving the way they conduct business with their key Trading Partners. Please find attached a letter, where you will find more information. Can you please confirm you EDI code, Message Type, Message Format, Version, Comm Type and Provider as attached. Premier Farnell will use new EDI Codes: Europe Region: Test: 5051259000285 Prod: 5051259000773 We plan to start testing in approx. 8 weeks. We will inform you before we start testing. If you are not the correct contact person in this matter, we would appreciate it if you could let us know whom we can reach out to. Please let us know if you need any clarification. Kind regards | Premier Farnell | Discovery | TP Coms Except | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-26
2.3 | EU | 3M UNITED KINGDOM PLC | 5013546030160 | 0 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | 3M-UK | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | IBM |  | cbuckley@tp1.com |  |  | TP never respond |  | Premier Farnell | Discovery | TP Coms Except | 27/10/2017 | 27/10/2017 | 13/12/2017 | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 06/09/2017 |  |  |  |  | 2018-02-26
2.3 | EU | 3M UNITED KINGDOM PLC | 5013546030160 | 0 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | 3M-UK | PINVOICE | INVOIC | IB | MQ | EDIFACT | D97A |  | VAN | IBM |  | cbuckley@tp1.com |  |  | TP never respond |  | Premier Farnell | Discovery | TP Coms Except | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_INVOIC_D97A_FP_GENERIC | Primary | E_INVOIC_D97A_FPX | 11/12/2017 | 31/10/2017 |  |  |  |  | 2018-02-26
1 | EU | ABB CONTROL LTD | ABB | 1 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ABB | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | FTP | B2BE |  | uk.support@tp2.com |  |  | survey received / received FTP file / TP informed new EDI codes of PF / comm test done, ready for E2E test | Email from TP - Hi, I confirm you that I received and sent your PO to UKABB: Email to TP - Hi Fabio, Can you pls confirm if you have received that first production ORDERS from Premier Farnell via IBM yesterday. UNB+UNOA:1+5051259000773+ABB+180115:2135+1++ORDERS'UNH+1+ORDERS:D:97A:UN:EDPO04'BGM+220+09163593+9'DTM+137:20180115:102 ... Go Live confirmed for 15th Jan 08.01.2018: 2nd reminder sent 04.01.2018: Email to TP - Hello Philip, Thank you for confirmation. Pls let us know if you are ready to go Live with new Premier Farnell ID's (Test : 5051259000285 Prod: 5051259000773) from Jan 15,2018. 03.01.2018 : Email from TP - Hi All Apologies for the delay – but we are now back at work after the Christmas Break . Having looked on our system I can certainly see the order as the attached acknowledgment has been received and processed without issue. Additionally, I have today generated an ORDRSP message which has been transmitted on IDOC = 15156831 BR 21.12.2017: Email from TP - ABB Controls have confirmed receipt of our file, validation pending .21.12.2017 Email to TP - Hi Fabio, The attached file has been sent successfully to ABB via the Test FTP connection. Could you confirm the receipt of the file on your side and also to validate the same? 21.12.2017: Email form TP - File received. I uploaded the attached file 21.12.2017: Email to TO - Hi Fabio, We have send you the attached file via the Test connection.Can you please confirm the receipt of the file on your side and also pls let us know if you would like to return back a file to us (though we understand that we have only data flowing from Premier Farnell to ABB Controls for now )? Also, please confirm if we can send them a similar file via the Production connection as well. Post the completion of the connectivity testing,we would be sending you the ORDERS file in Test for you to validate.20.12.2017: Email to TP - Hello Fabia, I do confirm that you need to change ONLY UNB segment and not any other change. As you mentioned you ( ABB) can continue to act as FTP server , but kindly share your details ( such as FTP user name and password) so that we can connect to your FTP server to send Order files to you. FTP form attached 18.12.2017: Email from TP - Hi, For the moment for Farnell we are using our FTP server (ftpext.it.abb.com) and we can’t change it. I would like to keep all as is. No problem to change the UNB record. Could you pls confirm me that we have to change ONLY the UNB value without any other change (FTP or EDIFACT specification or something else)? 14.12.2017: 3rd Reminder sent 08.12.2017: Followup sent to TP 23.11.2017 Email form Antje: Info: incorrect FTP account configured at IBM (gateway.b2be.com; should be ftpext.it.abb.com) PF will check for new / correct contact details. 23.11.2017 TP's response forwarded to Antje for clarification.17.11.2017 Email to TP: sent 1st reminder for data test. 16.11.2017 Email from TP: A Support Ticket: 3070360 has been successfully logged with the Support Team at 16/11/2017 01:28:02 with the detail as below: They will come back until ende of 16.11.2017 24.10.2017: Email to TP - Hello Darren,We have successfully sent the attached file to your PRD and TEST system, Can you pls check and confirm the receipt of the file. 18.10.2017: Email from TP : Hi I have checked and it looks like there was a problem with the length of the login previously. Please try farnellar-uk 12.10.2017 : Email to TP : Hello Darren, We are unable to connect to your FTP with below details provided. Host : gateway.b2be.com User Id: premierfarnellar-uk Password: PePoji71 Host : gatewayuat.b2be.com User Id: premierfarnellar-uk Password: PePoji7 Can you pls check and confirm if these are the correct FTP credentials to be used 10.11.2017: Email to TP Hello Darren, We have completed the Test and Production FTP setup for ABB now. Could you please let us know if you are ready to do the connectivity testing with us. Also please let us know if below mentioned IP addresses have been unblocked on your firewall? 159.122.87.167 159.122.87.16810.10.2017 Email to TP: Thank you for providing us the details. We will get in touch with you when we have done the set up on our side. 10.10.2017 Email to Anuj and Jas: Informed - FTP details 10.10.2017 Email from TP: Provide us FTP details. 04.10.2017 Email from TP: I'll forward this to Darren, your relationship manager to answer the questionnaires. 04.10.2017 Email to TP: Can you please reply to our request below and fill out the FTP questionnaire in the next 3 day's. Also I want to request the message type from ABB. We get the information from our Client Premier Farnell that ORDERS will be sent. Could you please also confirm this? We want to inform you that Premier Farnell is using new EDI Codes: Prod: 5051259000773 without qualif. Test : 5051259000285 without qualif. Please set up this new EDI Codes from Premier Farnell in your system that when we go live we don't have issues with data running. Please contact your VAN provider B2BE and request the set up of Premier Farnell's new EDI codes (Test : 5051259000285 Prod: 5051259000773 without qualif) on the IBM/Sterling VAN: this will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We ill inform you when we start testing. 29.09.2017 cs Email from TP: Thank you for contacting B2BE. A Support Ticket: 2988932 has been successfully logged with the Support Team at 29/09/2017 17:39:01 with the detail as below: 29.09.2017 cs Email to TP kindly remider for FTP uestionnaire. 26.09.2017 cs Email to TP: Kindly reminder - Could you please reply to our request below? Can you please reply to our request below and fill out the FTP questionnaire? Also I want to request the message type from ABB. We get the information from our Client Premier Farnell that ORDERS will be sent. Could you please also confirm this? We want to inform you that Premier Farnell is using new EDI Codes: Prod: 5051259000773 without qualif. Test : 5051259000285 without qualif. Please set up this new EDI Codes from Premier Farnell in your system that when we go live we don't have issues with data running. Please contact your VAN provider B2BE and request the set up of Premier Farnell's new EDI codes (Test : 5051259000285 Prod: 5051259000773 without qualif) on the IBM/Sterling VAN: this will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We ill inform you when these new ID's become effective closer to date. 15.09.2017 cs Email from TP: Apologies. I am out of the office. I will get this back to you on Monday, 15.09.2017 CS. 1st reminder: we haven't heard back from you since our last Email from 12.09.2017. Can you please reply to our request below and fill out the FTP questionnaire? Also I want to request the message type from ABB. We get the information from our Client Premier Farnell that ORDERS will be sent. Could you please also confirm this? 12.09.2017 DL: Sent FTP Questionnaire to the ABB. 06.09.2017 CS: Dharshan conf. that EDI is on our system. 31.08.2017 CS Email from Andre: PF confirmed that they only have orders. 31.08.2017 CS Email to Andre: request to check message type which they use - TP said INVOICE- 29.08.2017 cs Email to Dharshan: set up in IBM system. 24.08.2017 cs Email from Provider: Please find attached completed form. Please note that B2BE are ABB’s EDI provider but have added ABB contact email address to the form as requested. 24.08.2017 CS Email to Provider: could you please compete the request and also can you please provide me an Email address from ABB EDI department if we have any requests to them? 18.08.2017 Email from Craig to Tina and Andre: My conversation was with B2BE. the contact address came from yourselves. They werent sure who should complete either but committed to fill out in the first instance and see whether further comms with ABB were required subsequently. 18.08.2017 Email from Tina to Craig: You mentioned on the call yesterday you had spoken with ABB . The email contact we have is their EDI provider, 18.08.2017 Email to Tina: I get a feedback from ABB EDI partner. They don't use VAN interconnect. Should they sent it to ABB directly or do we have to ask PF, Andre Hill? 18.08.2017 Email to TP: yes, could you please fill out the document? 17.08.2017 Email form TP: We have received a request to complete your EDI Commerce Survey form for Premier Farnell for ABB invoices. We are ABB’s EDI partner and as we understand it, the existing EDI format and connection method will not change, excepting the GLN reference. We do not use a VAN interconnect. Should we complete the form or should ABB? 16.08.2017 Email from TP: We have forwarded your request to your account manager. He will take a look on this and will get back to you as soon as possible. 16.08.2017 Email form TP: sent ticket no 2899279 16.08.2017 CS. Email to TP: sent out reminder for lette and survey 09/Aug - DL - Sent the letter and survey | Premier Farnell | Live | Live | 27/10/2017 | 27/10/2017 |  | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 23/08/2017 |  |  | 20.11.2017 | 09.01.208 |  | 2018-01-15 | 2017-12-01 | 2018-01-15
2.2 | EU | ACAL ELECTRONICS | 5013546058072 | 1 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ACAL | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | uk.support@tp2.com |  |  | Ready to start E2E testing | 09.02.2018 4th reminder sent with new template 07.02.2018 - 3rd Followup sent 05.02.2018: Followup email sent 02.02. Email to TP - Confirmation sent copying Craig @ PF 02.02. EMail from TP : - Kusum – Please could you send Sales a confirmation from Premier Farnell saying you are authorised to contact us on their behalf? 02.02.2018 - 3rd Reminder sent 31.01.2018: 2nd reminder sent 29.01.2018: Sent E2E testing email 22.09.2017 Email to TP: inform TP - new contact details of PF 21.09.2017 Email from TP: sent back survey. 21.09.2017 Email to TP sent out 2nd reminder 18.09.2017 Email from TP: sent survey. Please could you have a look the attached survey and return it to the client ? 13.09.2017 Email to TP sent out 1st reminder 07.09.2017: Email to TP: sent out letter and survey to TP. | TP | E2E Testing | TP Coms Except | 27/10/2017 | 27/10/2017 | 13/12/2017 | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 06/09/2017 |  |  |  |  | 2018-02-19
2.2 | EU | ACAL ELECTRONICS | 5013546058072 | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 | ZZ | ACAL | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | uk.support@tp2.com |  |  | Ready to start E2E testing | 09.02.2018 4th reminder sent with new template 07.02.2018 - 3rd Followup sent 05.02.2018: Followup email sent 02.02. Email to TP - Confirmation sent copying Craig @ PF 02.02. EMail from TP : - Kusum – Please could you send Sales a confirmation from Premier Farnell saying you are authorised to contact us on their behalf? 02.02.2018 - 3rd Reminder sent 31.01.2018: 2nd reminder sent 29.01.2018: Sent E2E testing email 22.09.2017 Email to TP: inform TP - new contact details of PF 21.09.2017 Email from TP: sent back survey. 21.09.2017 Email to TP sent out 2nd reminder 18.09.2017 Email from TP: sent survey. Please could you have a look the attached survey and return it to the client ? 13.09.2017 Email to TP sent out 1st reminder 07.09.2017: Email to TP: sent out letter and survey to TP. | TP | E2E Testing | TP Coms Except | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-19
2.2 | EU | ADVANCED TRADING COMPANY | farnell@argussoft.ru | 1 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ARGUSSOFT | INVOICES | INVOIC | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | SMTP |  |  | accountingdesk@tp3.com |  |  | Ready for GO Live on 12.02.2018 | 09.02.2018 Email from TP - Yes we confirm that we will go -live on Monday, 12-Feb. at 10.00 GMT with Premier Farnell via IBM 08.02.2018 Email toTP: Can you please confirming that you will go -live on Monday, 12-Feb. at 10.00 GMT with Premier Farnell via IBM. NOTE - the Premier Farnell Production EDI code will change from 5013546005195 -> 5051259000773, so please your internal records for this partner accordingly. 06.02 Test file sent to TP , TP yet to confirm receipt 05.02 TP confirmed ready to test 02.02. Email to TP - Confirmation sent copying Craig @ PF 02.02. EMail from TP : - Kusum – Please could you send Sales a confirmation from Premier Farnell saying you are authorised to contact us on their behalf? 02.02.2018 - 3rd Reminder sent 31.01.2018: 2nd reminder sent 29.01.2018: Sent E2E testing email 22.09.2017 Email to TP: inform TP - new contact details of PF 21.09.2017 Email from TP: sent back survey. 21.09.2017 Email to TP sent out 2nd reminder 18.09.2017 Email from TP: sent survey. Please could you have a look the attached survey and return it to the client ? 13.09.2017 Email to TP sent out 1st reminder 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | Live | Live | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_O_E_INVOIC_D97A_F10 | Primary | E_INVOIC_D97A_F10 | 11/12/2017 | 23/10/2017 |  |  |  |  | 2018-02-19 | 2018-02-12 | 09/02/2018 | 2018-02-12
1 | EU | KEYSIGHT TECHNOLOGIES | AGILENT2010 | 1 | new ID: no qualif. ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AGILENT-INST | INVENTORY | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR | FTP | Entomo FTP |  | g.shivaraj@tp4.com (Gayathri Shivaraj) and l.vuong@tp4.com (Luan Vuong) |  |  | received FTP questionnaire / TP is informed new EDI codes from PF / TP confirmed test/ | 07.12.2017: Email to TP - This is great news ! Thank you for confirmation Luan. 07.12.2017: EMail from TP - Hi Kusum, We did receive and processed the INVRPT report yesterday. Please the attached screen shot below for confirmation the file was processed in the system. Thanks, Luan 07.12.2017: Email to TP - Hello Luan, We have sent our first production INVRPT via IBM yesterday (6-Dec.) at 17.24 GMT with ICN 1. UNB+UNOA:1+5051259000773+AGILENT2010:ZZ+171206:1724+1++INVRPT' UNH+1+INVRPT:D:97A:UN:EDDS02' BGM+35+201712061712563+9' . Can you pls check and confirm the receipt of the same.06.12.2017: Email to TP - Hello Laun, Premier Farnell will submit a new INVRPT with a new date (but possibly same data) either today or tomorrow. We will let you know once the file has been sent via IBM. 29.11.2017: Email from TP - Hi Kusum, We have processed the test INVPRT successfully in our system. Please see the attached screenshot below as confirmation of the test file processed successfully. 28.11.2017: Email to TP - Hello Luan, Pls confirm if you are able to process the INVPRT messages we sent you at your end successfully . Also we are unable to review the CSV you sent as we are able to send only outbound INVRPT messages to you and no incoming messages from Keysight to Premier Farnell. 27.11.2017 - Email from TP - Hi Dharshan, We did receive the test file on 11/21/2017 from the FTP directory location. We have completed translating the test file into CSV format for processing. Please review the attached CSV file and let us know if anything is incorrect. 23.11.2017 1st reminder to TP on E2E testing.17.11.2017 Email to TP: The maps are specific to Premier Farnell. We will sent test files on 20th Nov. 17.11.2017 Email to Anuj: ask to check 16.11.2017 Email form TP: Sending the test file to the FTP directory location would be fine. Would you be able to send us the translation maps you have performed? 14.11.2017 Email to TP Based on confirmation from implemenation, Dear Laun I have communicated this to our implementation team. The will name the files as test when sending the test files. 09.11.2017 Email from Tp:Hi Kusum, Thank you for suggesting the 2 options below. We are proposing a third option and hope you will be able to work with it. The same ftp location can be used for the testing as we have done this in the past successfully. However, we would need to only rename the file appropriately. For testing please include in the file name “test”. This will designate it as a test file. When it is time to go to production the file names will need to be named “INVRPT” accordingly to be processed correctly.Thanks, Luan06.11.2017: Email to TP - Hello Luan,We found that you have same FTP details for both test and production, This could be a problem in future. We propose two ways :1. Provide us details of a different test FTP ( different IP/URL and username /password than of Production server) 2. In case you have same server for both test and production create separate folder for sending test and production files. 24.10.2017: Email from TP - Hi Kusum,We did receive the test files on the ftp at this directory location: /toEntomo/inv. Please continue to use this location.Thanks,Luan24.10.2017: Email to TP : Hello Luan,Can you pls confirm if you have received the test files we sent you on 11th October. 11.10.2017: Email to TP : Hi Luan We have now completed the Test and Prod FTP setups for Keysight Technologies and also able to send you a dummy file from the Test and Prod Business Aliases of Premier Farnell. Since you would be using the same FTP parameters for both Test and Prod environments, you should see two files with the names given below as delivered in the /toEntomo/in directory of your FTP server. Test_KEYSIGHT.txt Test_KEYSIGHT_Prod.txt Could you please confirm if you would continue to use the same folder for receiving the test and production files from Premier Farnell or else you need to create a separate folder for the test environment and provide us those details. Also, request you to confirm the receipt of the 2 files on your side.10.10.2017 Team call: waiting feedback from Anuj regarding FTP file for the TP. 19.09.2017 cs Email to TP: we will inform you when we start testing. 19.09.2017 cs Email from TP: Please confirm when Premier will be sending us the INV file with the new EDI code below. Can you provide us with a sample test file with the new code? 18.09.2017 cs Email to TP: Informed TP that PF use new EDI codes. thank you for sending the FTP questionnaire. Also we want to inform you the Premier Farnell will use new EDI codes. Prod: 5051259000773 Test : 5051259000285 Could you please set up this in your system that when we go live that we have no issues with data running? 15.09.2017 CS Email from TP: Please see that attached FTP questionnaire. 15.09.2017 cs: sent reminder FTP Questionnaire 12.09.2017 DL: Sent FTP Questionnaire 06.09.2017 CS: Email from Dharshan EDI is present in our system. 29.08.2017 cs Email to Dharshan: set up in IBM system. 28.08.2017 cs Email from TP: Production Id: AGILENT2010 Qualifier: ZZ Below is a sample of the header EDIFACT INVRPT information we are receiving from Premier: UNB+UNOA:1+5013546005195+AGILENT2010:ZZ+170819:0219+000355++INVRPT We currently don’t have any Test Id and Qualifier setup. 28.08.2017 cs. Email to TP: Can you please give us the the Production ID and Qualifier from KEYSIGHT TECHNOLOGIES and also let us know if you got a Test Id and Qualifier. 23.08.2017 cs. TP sent back survey. Please find attached our response to the Premier Farnell survey document. Our responses attached is based on the current process we are doing for Premier Farnell. If there are additional requirements and specifications needed please provide sample files and required specifications so that we can implement. 21.08.2017 cs: sent 1st reminder letter and survey 16.08.2017 cs: sent email to TP letter and survey 16.08.2017 cs Email from Andre Hill: provide contact details. 16.08.2017 cs- Email from Andre Hill: Someone at Keysight has contacted the person he thinks would be correct for us but that person is away until the 21st so he can’t confirm anything until next week. 16.08.2017 CS_ Email to Andre Hill: new TP where we need new contact details and reminder. 10.08.2017 CS: Email to Andre Hill: need contact details. AHill@premierfarnell.com 09/Aug - DL - No contact details. Must check with Corinna | Premier Farnell | Live | Live | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_O_E_INVRPT_D97A_FA9 | Primary | E_INVRPT_D97A_FA9 | 08/12/2017 | 14/09/2017 |  |  | 20.11.2017 | 20.11.2017 |  | 2017-12-04 | 2017-12-01 | 2017-12-04
2.3 | EU | AIRBUS GERMANY | AIRBUS DE | 1 | ZZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 | 14 | AIRBUS-DE | ASN | DESADV | OB | MQ | EDIFACT | D97B | INS/UNOB/FAR | X.400 | VIAT | C=WW, A=AIN, P=AIRBUS, O=M2M, S=PROD | Rebecca VOGELEY (no email) | +49 (0)40 743 77122 |  |  | 12.02.18 attempt to call Mr. Vogeley -no response. 04.12.2017 try to call Airbus Germany: they don't give out Email adresses, Customer has to contact them. | CDS | Discovery | Waiting on TP Coms1 | 2017-03-10 | 2017-03-10 | 2017-06-10 |  |  | PF_O_E_DESADV_D97B_FAR | Primary | E_DESADV_D97B_FAR | 10/01/2018 | 31/10/2017 | 31/10/2017 |  |  |  | 2018-02-26
2.3 | EU | AIRBUS GERMANY | AIRBUS DE | 0 | ZZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 | 14 | AIRBUS-DE | INVOICES | INVOIC | OB | MQ | EDIFACT | D93A | INS/UNOB/FAR | X.400 | VIAT | C=WW, A=AIN, P=AIRBUS, O=M2M, S=PROD | Rebecca VOGELEY (no email) | +49 (0)40 743 67122 |  |  | 12.02.18 attempt to call Mr. Vogeley -no response. 04.12.2017 try to call Airbus Germany: they don't give out Email adresses, Customer has to contact them. | CDS | Discovery | Waiting on TP Coms1 | 2017-09-10 | 2017-09-10 | 17/10/2017 |  |  | PF_O_E_INVOIC_D93A_FA3 | Primary | E_INVOIC_D93A_FA3 | 11/12/2017 | 23/10/2017 |  |  |  |  | 2018-02-26
3 | EU | ALPHAWIRE | 056707714 | 1 | 01 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ALPHAWIRE | LTUPDATE | INVRPT | IB | SFTP | EDIFACT | D97A |  | VAN | GXS |  | Tom.Behr@alpha.com |  | reminder 15.12.2018 | Survey Received | 08.02.2018 TP shared GXS contact number, could not reach, sent mail to TP asking for the same 29.01.2018: Ftp Questionaire sent 26.01.2017 Email to TP: sent out first letter and survey | Implementer | TP Setup | TP Setup | [7 empty] | E_INVRPT_D97A_FAM
3 | EU | ALPHAWIRE | 056707714 | 0 | 01 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ALPHAWIRE | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | Tom.Behr@alpha.com |  |  | Survey Received |  | Implementer | TP Setup | TP Setup | 2017-10-10 | 2017-10-10 | 18/10/2017 |  |  | PF_O_E_ORDERS_D97A_FA8 |  | E_ORDERS_D97A_FA8 | 05/12/2017 | 31/10/2017
3 | EU | ALPHAWIRE | 056707714 | 0 |  | Test : 5051259000285 Prod: 5051259000773 |  |  |  | ALPHAWIRE | PEITRAN |  | IB | SFTP |  |  |  | FTP | GXS |  | Tom.Behr@alpha.com |  |  | Survey Received / File Routing only |  | TP | TP Setup | Waiting on TP Coms2 |  |  | N/A | N/A | N/A | N/A | N/A | N/A - File to be routed | N/A - File to be routed
3 | EU | ALPHAWIRE | 056707714 | 0 | 01 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ALPHAWIRE | PINVOICE | INVOIC | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | Tom.Behr@alpha.com |  |  | Survey Received |  | Implementer | TP Setup | TP Setup | 2017-05-10 | 2017-05-10 | 17/10/2017 |  |  | PF_I_E_INVOIC_D97A_FP_GENERIC | Primary | E_INVOIC_D97A_FPE | 11/12/2017 | 31/10/2017
3 | EU | ALPHAWIRE | 056707714 | 0 | 01 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ALPHAWIRE | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | Tom.Behr@alpha.com |  |  | Survey Received |  | Implementer | TP Setup | TP Setup | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017
3 | EU | ALPHAWIRE | 056707714 | 1 | 01 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ALPHAWIRE-STOCK | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR/ALPH | VAN | GXS |  | Tom.Behr@alpha.com |  |  | Survey Received |  | Implementer | TP Setup | TP Setup | 2017-10-10 | 2017-10-10 | 18/10/2017 |  |  | PF_O_E_ORDERS_D97A_FA8 |  | E_ORDERS_D97A_FA8 | 05/12/2017 | 31/10/2017
2.3 | EU | AMPHENOL INFOCOM | AOM50213 | 1 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AMPHENOL-INFOCOM | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | order@amphe.com |  |  | received survey / TP is infomed new PF EDI codes | 01.02.2018 Email from TP. sent survey back. 01.02.2018 Email to TP: sent reminder 25.01.2018 Email to TP: sent out letter and survey. 26.01.2018 new contact details from PF. back to PF: old Email address from TP: order@amphenol.nl / never respond 02.11.2017: Email to TP - Remainder sent 26.10.2017: Email to TP, TP Survey and Intro letter sent again in new template23.10.2017: Email to TP 7th Remainder sent 17.10.2017: Email to TP 6th Remainder sent 12.10.2017 : Email to TP - 5th Remainder email sent 10.09.2017: Email to TP 4th Remainder sent .27.09.2017 Email to TP sent out 3rd reminder 21.09.2017 Email to TP sent out 2nd reminder 18.09.2017 Email to TP sent out 1st reminder 13.09.2017: Email to TP: sent out letter and survey to TP. | Implementer | TP Setup | TP Setup | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-26
2.3 | EU | AMPHENOL INFOCOM | AOM50213 | 0 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AMPHENOL-INFOCOM | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | order@amphe.com |  |  | received survey / TP is infomed new PF EDI codes |  | Implementer | TP Setup | TP Setup | 31/07/2017 | 31/07/2017 | 2017-07-08 | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 06/09/2017 |  |  |  |  | 2018-02-26
2.3 | EU | AMPHENOL INFOCOM | AOM50213 | 0 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AMPHENOL-INFOCOM | PINVOICE | INVOIC | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | order@amphe.com |  |  | received survey / TP is infomed new PF EDI codes |  | Implementer | TP Setup | TP Setup | 2017-05-10 | 2017-05-10 | 17/10/2017 |  |  | PF_I_E_INVOIC_D97A_FP_GENERIC | Primary | E_INVOIC_D97A_FPE | 11/12/2017 | 31/10/2017 |  |  |  |  | 2018-02-26
2.1 | EU | AMPHENOL TUCHEL ELECTRONICS | AMPHOFTP | 1 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AMPHENOLTUCHEL | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | AS2 |  |  | order@tp6.com |  | E2E complete/ GL confirmed | Ready for GO Live on 12.02.2018 | 14.02 LIVE order sent, TP confirmed receipt 13.02 TP sent first Live ORDRSP messages, PF to confirm when first LIVE Order will be sent 09.02.2018 Email from TP - Dear Corinna, I confirm that we will go live with EDI-connection on Monday 12-Feb. at 10.00 GMT with Premier Farnell via IBM. 08.02.2018 Email form TP. [#20180208-2181 Ticket Number 08.02.2018 Email to TP: Can you please confirming that you will go -live on Monday, 12-Feb. at 10.00 GMT with Premier Farnell via IBM. NOTE - the Premier Farnell Production EDI code will change from 5013546005195 -> 5051259000773, so please your internal records for this partner accordingly. 05.02. TP confirmed GL for 12 Feb 05.02. Received ORDRSP file. 05.02.2018: Email to TP - Hello Lucas, We have received your file in encoded format. Can you pls resend the file to us in ANSI format. 02.02.2018: TP sent test file with incorrect ID, asked them to correct and resend 31.01.2018: TP confirmed receipt of order, waiting for ORDRSP 31.01.2018: TP informed ready to test 31.01.2018 Email to Tp 2nd followup on E2E Testing29.01.2018 E2E testing email sent.24.01.2018: Dear Trading Partner, Premier Farnell and IBM are now in a position to test the newly developed EDI maps and we would like to invite you to test the EDI messages. Your Go-live has been scheduled for the w/c 12-Feb-18, assuming all tests are successful. Please let me know if you are ready to receive Test messages for ORDER documents you exchange with Premier Farnell via your preferred method of connection. We would also like to receive Test files from you (ORDRSP).The Test files will be sent to Farnell's new Test EDI code as well a Test Indicator: Test : 5051259000285 (EU) Thank you for your co-operation on this important project. Kind regards,Kusum Kumar. 09.01.2018: Email to TP - Hello Lucas, Can you pls confirm if the prod identifier is Amphenol-Tuchel_Prod or Amphenol_Tuchel_Prod( corresponding to test identifier). 09.01.2018: Email from TP - Hello, the URL looks fine to me, the ID was a bit wrong - it should be: Amphenol_Tuchel_Test - for test Amphenol-Tuchel_Prod - for prod Apart from that you can start testing the connection, please let me know when the first message should have arrived.08.01.2018: EMail to TP - Hi Team, We were able to complete the Test AS2 setup now for Amphenol-Tuchel and we need to check if you also have the setup ready on your side so that we can have a round of connectivity testing. Below are the details that were used for doing the setup. Can you also pls confirm on the below given AS2 Id's and URL's as well? Premier Farnell AS2 ID: PREMIERFARNELL_TEST URL: http://premierfarnell.as2.b2b.ibmcloud.com/as2 Amphenol-Tuchel AS2 ID: Amphenol-Tuchel_Test URL: https://gateway-as2.txx.seeburger.de/as2_prod 23.11.2017 Email to TP:we'll get on it and configure the AS2 connection and get back to you once done. 20.11.2017 Email to Antje: Do let us know if a follow up can be sent today. 13.11.2017 Email from TP: unsere IT hat die Firewall freigeschaltet - können Sie bitte versuchen eine ORDERS von Seiten Premier-Farnell an Amphenol zu senden und mich über das Ergebnis des Tests informieren? Sobald wir die ORDERS vorliegen haben werde ich mit Amphenol die Verarbeitung prüfen und eine ORDRSP zurücksenden. 09.11.2017 Email from TP (Seeburger- Provider): vielen Dank für die bereitgestellten Informationen. SEEEBURGER ist nur für Amphenol Tuchel Electronics verantwortlich. Ich habe unsere IT gebeten unsere Firewall entsprechend Ihres Datenblattes zu konfigurieren. Sobald ich Rückmeldung von unserer IT habe melde ich mich wieder bei Ihnen um die Verbindung zu testen. 08.11.2017: Email to TP - Hallo Herr Noack, Is Seeburger auch für die Amphenol Infocom (EDI code AOM50213) verantwortlich ? Wenn ja, ändern wir gerne für beide Amphenol Partner die Verbindung auf AS2. Anbei unser AS2 Fragebogen und Zertifikate. Die Premier Farnell EDI codes werden sie im Zuge der Migration zu IBM ändern: Neue Test ID: 5051259000285 Neue Prod ID: 505125900077306.11.2017: Email to TP - Hello Team, As per our records Amphenol Tuchel uses GXS VAN to communicate with Premier Farnell. But you shared AS2 details with us. Are you planning on changing comm type as AS2 instead of VAN or info we have is incorrect. Pls confirm. Also we noted that AS2 details and certificate for test are missing, pls send us AS2 details for TEST . In case you have same details for TEST and PROD, pls do let us know the same.06.11.2017: Email from TP - sent AS2 details and certificates26.10.2017: Email to TP, TP Survey and Intro letter sent again in new template23.10.2017: Followup email sent.17.10.2017: Email from Seeburger to Amphenol : Dear Customer, Could you please check the email below and let us know if any assistance from SEEBURGER end is required? Thank you! Best regards / Mit freundlichen Grüßen, Kiril Gotsev Cloud Service Team17.10.2017: Email to TP 6th Remainder sent 12.10.2017 : 5th remainder email sent to TP 10.09.2017: Email to TP 4th Remainder sent .27.09.2017 Email to TP sent out 3rd reminder 21.09.2017 Email to TP sent out 2nd reminder 18.09.2017 Email to TP sent out 1st reminder 13.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | Live | Live | 31/07/2017 | 31/07/2017 | 2017-07-08 | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 06/09/2017 |  |  |  |  | 2018-02-12 | 2018-02-12 | 09/02/2018 | 12/02/2018
2.1 | EU | AMPHENOL TUCHEL ELECTRONICS | AMPHOFTP | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AMPHENOLTUCHEL | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | AS2 |  |  | order@tp6.com |  |  | Ready for GO Live on 12.02.2018 |  | Premier Farnell | Live | Live | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-12 | 2018-02-12 | 09/02/2018 | 12/02/2018
2.3 | EU | ANALOG DEVICES LTD | ANALOG DEVICES | 1 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ANALOG-DEVICES | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | stefan.karlsson@log.com |  |  |  | 18.09.2017 Email from Antje: The feedback I have is that we should remove ANALOG-DEVICES, and ANALOG-DEVICES-SG from scope. 15.09.2017 Email from Antje: Status: TP said that they are no longer trading with PF, effective 27-Oct. Waiting for clarification from client. 14.09.2017 Email to Antje: diese Info haben wir zurück von ANALOG DEVICES LTD dazu gehört auch ANALOG DEVICES TAIWAN, wurde uns der gleich Ansprechpartner von PF genannt. Gehe mal davon aus das wir diese Info zurück an PF geben müssen und um neue Kontakt Daten fragen- richtig? Please be aware that Analog Devices has recently terminated its franchised relationship with Premier Farnell, effective 27th October, and we will therefore not be responding to your survey request.07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | De-scoped | De-scoped | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FAR
2.3 | EU | ANALOG DEVICES LTD | ANALOG DEVICES | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ANALOG-DEVICES | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | stefan.karlsson@log.com |  |  |  | 18.09.2017 Info form Antje und Andre: The feedback I have is that we should remove ANALOG-DEVICES, and ANALOG-DEVICES-SG from scope. 15.09.2017 Email from Antje: Status: TP said that they are no longer trading with PF, effective 27-Oct. Waiting for clarification from client. 14.09.2017 Email to Antje: diese Info haben wir zurück von ANALOG DEVICES LTD dazu gehört auch ANALOG DEVICES TAIWAN, wurde uns der gleich Ansprechpartner von PF genannt. Gehe mal davon aus das wir diese Info zurück an PF geben müssen und um neue Kontakt Daten fragen- richtig? Please be aware that Analog Devices has recently terminated its franchised relationship with Premier Farnell, effective 27th October, and we will therefore not be responding to your survey request.07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | De-scoped | De-scoped | 2017-04-08 | 2017-04-08 | 2017-10-08 | 21/8/2017 | 24/08/2017 | PF_O_E_ORDERS_D97A_FAR | Primary | E_ORDERS_D97A_FAR
2.3 | EU | ANALOG DEVICES LTD | ANALOG DEVICES | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ANALOG-DEVICES | POINTOS | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AD | VAN | GXS |  | stefan.karlsson@log.com |  |  |  | 18.09.2017 Info form Antje und Andre: The feedback I have is that we should remove ANALOG-DEVICES, and ANALOG-DEVICES-SG from scope. 15.09.2017 Email from Antje: Status: TP said that they are no longer trading with PF, effective 27-Oct. Waiting for clarification from client. 14.09.2017 Email to Antje: diese Info haben wir zurück von ANALOG DEVICES LTD dazu gehört auch ANALOG DEVICES TAIWAN, wurde uns der gleich Ansprechpartner von PF genannt. Gehe mal davon aus das wir diese Info zurück an PF geben müssen und um neue Kontakt Daten fragen- richtig? Please be aware that Analog Devices has recently terminated its franchised relationship with Premier Farnell, effective 27th October, and we will therefore not be responding to your survey request.07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | De-scoped | De-scoped | 19/9/2017 | 19/9/2017 | 29/9/2017 |  |  | PF_O_E_SLSRPT_D97A_FA_GENERIC | Primary | E_SLSRPT_D97A_FA4
2.3 | EU | ANALOG DEVICES TAIWAN | 001418417ASIA | 1 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ANALOG-DEVICES-SG | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | stefan.karlsson@log.com |  |  |  | 18.09.2017 Email from Antje: The feedback I have is that we should remove ANALOG-DEVICES, and ANALOG-DEVICES-SG from scope. 15.09.2017 Email from Antje: Status: TP said that they are no longer trading with PF, effective 27-Oct. Waiting for clarification from client. Please be aware that Analog Devices has recently terminated its franchised relationship with Premier Farnell, effective 27th October, and we will therefore not be responding to your survey reques | Premier Farnell | De-scoped | De-scoped | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FAR
2.3 | SG | ANALOG DEVICES TAIWAN | 001418417ASIA | 0 | ZZ | Test: 5051259000377 Prod:5051259000865 |  | 5013546005195 |  | ANALOG-DEVICES-SG | PORDERSG | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | stefan.karlsson@log.com |  |  |  | 18.09.2017 Info form Antje und Andre: The feedback I have is that we should remove ANALOG-DEVICES, and ANALOG-DEVICES-SG from scope. 15.09.2017 Email from Antje: Status: TP said that they are no longer trading with PF, effective 27-Oct. Waiting for clarification from client. Please be aware that Analog Devices has recently terminated its franchised relationship with Premier Farnell, effective 27th October, and we will therefore not be responding to your survey reques | Premier Farnell | De-scoped | De-scoped | 2017-10-10 | 2017-10-10 | 18/10/2017 |  |  | PF_O_E_ORDERS_D97A_FAS |  | E_ORDERS_D97A_FAS
2.2 | EU | ARROW ELECTRONICS (UK) LTD | PROD : 5013546000488 TEST : ARROWEUTEST/ ZZ | 1 | UK21 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ARROW | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | Patrick Hagerty <PHagerty@tp7.com>, Ashley Tippett <ATippett@tp7.com>) tduft@tp7.com |  | reminder 14.02.2018( TP to confirm GL date 19th on Wednesday) | Ready to start E2E testing | 09.02 TP sent ORDRSP , agreed to go Live on 19th IF everything ok on their side. 09.02.2018 TP confirmed receipt of files, yet to send us ORDRSP 08.02.2018 Email to TP: Thank you for your confirmation. But at first we need to check if ORDRSP is running well. Do you have an idea when you sent this data? 08.02.2018 Email form TP: If everything is fine we can start 19.02.2018 / waiting for ORDRSP from TP to check. 08.02.2018 Email to TP: Thank you for your information. Please let us know when you have sent back a ORDRSP. When the tests are running well without issues can we plan a go live date for 19.02.2018. Can you please confirm this? 08.02.2018 Email from TP: Has been received and sent to our backend. 07.02.2018 Email to PF: TP is ready for testing. 07.02.2018 4th Reminder sent 02.02. 3rd reminder 31.01.2018: 2nd reminder sent 29.01.2018: Sent E2E testing email 09.11.2017 Email from TP, completed received. 08.11.2017: Email from ANder: new contact detail provided, TP survey and intro leter sent.02.11.2017: Email to TP - Remainder sent again 26.10.2017: Email to TP, TP Survey and Intro letter sent again in new template23.10.2017: Email to TP, Followup email sent 17.10.2017 Email from TP to their partner: Please would you advise regarding the previous email or pass to the correct person relating to this subject. (Patrick Hagerty <PHagerty@arroweurope.com>, Ashley Tippett <ATippett@arroweurope.com>) 12.10.2017 L: Email from TP I am out of the Office until 17th October and have no access to my Emails. Please contact the team if urgent on 01279 455355. Thanks for your patience.12.10.2017 Email to TP - Hello Melanie, We haven't heard back from your sales team yet, could you please share their email address, so that we can get in touch with them directly. 06.10.2017 Email from TP: I have forwarded your email to our sales team to action and they will contact you directly. 28.09.2017 Email to TP: 2nd Reminder 25.09.2017 1st Reminder sent to TP 20.09.2017 Email from TP: I have forwarded to our Sales team to review and if they are not the right contacts to pass onto the correct area of our business 18.09.2017 Email to TP sent out 1st reminder 14.09.2017 Email from Antje to TP: Thank you for your Email. Our client Premier Farnell UK is already trading electronically with Arrow Electronics. We only need to confirm that your EDI details are correct and if you are responsible for making EDI related configuration changes in your system. You should have received an Introduction letter informing you of the changes Premier Farnell is undertaking. Premier Farnell is moving to IBM as a managed Services client, along with the use of our VAN capabilities. Please contact your VAN provider GXS / OpenText and request the set up of Premier Farnell's new EDI codes - Test: 5051259000377 + Prod:5051259000865 at IBM / Sterling VAN (ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. The EDI code we have for Arrow Electronics is : 5013546000488 / qualifier UK21. Please confirm. 14.09.2017 Email zu Antje: ask Antje for next stepp 13.09.2017 Email from TP. We are not permitted to complete the survey as this is an Arrow company policy. 13.09.2017 Email to TP sent out 1st reminder 07.09.2017: Email to TP: sent out letter and survey to TP. | TP | Production Readiness | Production Readiness | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FAR | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-19 | 2018-02-19
2.2 | EU | ARROW ELECTRONICS (UK) LTD | PROD : 5013546000488 TEST : ARROWEUTEST/ ZZ | 0 | UK21 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | ARROW | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | Patrick Hagerty <PHagerty@tp7.com>, Ashley Tippett <ATippett@tp7.com>) tduft@tp7.com |  |  | Ready to start E2E testing |  | TP | Production Readiness | Production Readiness | 31/07/2017 | 31/07/2017 | 2017-07-08 | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 06/09/2017 |  |  |  |  | 2018-02-19 | 2018-02-19
2.2 | AU | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 1 | ZZ | Test : 5051259000292 Prod: 5051259000780 |  | 5013546005195 |  | AGILENT-SG | INVENTORYA | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  | Reminder 22.02.2018 | Ready to start E2E testing | 13/02,Email to TP - confirmed EDI ID, POINT#2 PF to clarify 12.02 : Email from TP - Hi,To further clarify, kindly advise on our enquires below.1. On your table list, there are 2 IDs stated for SG Region . Please confirm if these IDs are to be use. SG Prod - :5051259000780 & :5051259000865 SG Test - :5051259000292 & :5051259000377 Also noticed that on your Table, the ORDERS and ORDCHG are only for EU . What are the IDs to be used for SG ORDERS and ORDCHG? Please advise. 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1A | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | SG | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 0 | ZZ | Test : 5051259000292 Prod: 5051259000780 |  | 5013546005195 |  | AGILENT-SG | INVENTORYC | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  |  | Ready to start E2E testing | 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1C | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | SG | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 0 | ZZ | Test : 5051259000292 Prod: 5051259000780 |  | 5013546005195 |  | AGILENT-SG | INVENTORYI | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  |  | Ready to start E2E testing | 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1I | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | SG | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 0 | ZZ | Test: 5051259000377 Prod:5051259000865 |  | 5013546005195 |  | AGILENT-SG | INVENTORYS | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  |  | Ready to start E2E testing | 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1S | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | SG | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 0 | ZZ | Test: 5051259000377 Prod:5051259000865 |  | 5013546005195 |  | AGILENT-SG | POINTOSSG | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  |  | Ready to start E2E testing | 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 21/9/2017 | 21/9/2017 | 29/9/2017 |  |  | PF_O_E_SLSRPT_D97A_SG6 | Primary | E_SLSRPT_D97A_SG6 | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | SG | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 0 | ZZ | Test: 5051259000377 Prod:5051259000865 | SFTP | 5013546005195 |  | AGILENT-SG | POINTOSCN | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  |  | Ready to start E2E testing | 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 21/9/2017 | 21/9/2017 | 28/9/2017 |  |  | PF_O_E_SLSRPT_D97A_CN6 | Primary | E_SLSRPT_D97A_CN6 | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | SG | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 0 | ZZ | Test: 5051259000377 Prod:5051259000865 | SFTP | 5013546005195 |  | AGILENT-SG | POINTOSIN | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  |  | Ready to start E2E testing | 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 21/9/2017 | 21/9/2017 | 29/9/2017 |  |  | PF_O_E_SLSRPT_D97A_IN6 | Primary | E_SLSRPT_D97A_IN6 | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | AU | BROADCOM - Formerly AVAGO Technologies | 084963177GSPGN | 0 | ZZ | Test : 5051259000292 Prod: 5051259000780 |  | 5013546005195 |  | AGILENT-SG | POINTOSAU | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/AGIL | VAN | GXS |  | arthur-kc.puah@com.com |  |  | Ready to start E2E testing | 06.02 TP agreed to start tetsing on Feb 22 02.02. 3rd reminder sent 31.01.2018: 2nd reminder sent29.01.2018: Sent E2E testing email 18.09.2017 cs Email to TP: Thank you for the completed survey. Please note that with Premier Farnell's migration to IBM managed Service, they will change the EDI codes in the UNB records. You must contact your VAN provider GXS/OpenText and request the set up of Premier Farnell's new EDI codes (see below) on the IBM / Sterling VAN (interconnect ABJ08601). This will ensure the continuous flow of production messages, once Premier Farnell goes live on the IBM/Sterling network. We will inform you when these new ID's become effective closer to date. Depending on the delivery region, there will be two new EDI codes respectively. We are expecting all data from Broadcom / Avago Technologies via your current ID 084963177GSPGN. EU Region: New Premier Farnell Test EDI: 5051259000285 New Premier Farnell Prod EDI: 5051259000773 Australia Region: New Premier Farnell Test EDI : 5051259000292 New Premier Farnell Prod EDI: 5051259000780 Singapore Region: New Premier Farnell Test EDI: 5051259000377 New Premier Farnell Prod EDI:5051259000865 Your EDI Code: 084963177GSPGN Sample data for your reference: UNA:+.? ' UNB+UNOA:1+084963177GSPGN:ZZ+5013546005195+170913:0959+100049769++DESADV' UNH+0004976900001+DESADV:D:97A:UN:EDDS07' BGM+351+22107412+9' DTM+137:20170913:102' UNB+UNOA:1+5013546005195+084963177GSPGN:ZZ+170912:1604+003907+PFREM15P+ORDERS' UNH+0000001+ORDERS:D:97A:UN:EDPO04' BGM+220+08979766+9' DTM+137:20170912:102' NAD+BY+FARNELL-GB1::92++FARNELL' Should you have further questions, do not hesitate to contact me. 15.09.2017 cs Email : Andre sent sample files . Waiting for feedback Antjek. 07.09.2017: Email to TP: sent out letter and survey to TP. | Premier Farnell | E2E Testing | E2E Test Slot Agreed | 21/9/2017 | 21/9/2017 | 28/9/2017 |  |  | PF_O_E_SLSRPT_D97A_AU6 | Primary | E_SLSRPT_D97A_AU6 | 12/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.2 | EU | AVNET LTD | AVNETUK | 1 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVNET | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | Inovis |  | Mark.Mcgill@xyz.com |  |  | Ready to start E2E testing | 7.2.18 comms escalated to client. 07.02.2018 Reminder sent in new template 06.02.2018 4th reminder to TP 02.02 3rd rerminder sent 31.01.2018: 2nd reminder sent 29.01.2018: Sent E2E testing email 12.10.2017 Email to TP: Thank you for providing us the survey. We will get in touch with you when we start testing in approx. 8 weeks. 12.10.2017 Email form TP. received survey 09.10.2017: Email to TP 5th Remainder sent 04.10.2017 : 4th Remainder sent to TP 27.09.2017 Email to TP sent out 3rd reminder 21.09.2017 Email to TP sent out 2nd reminder 18.09.2017 Email to TP sent out 1st reminder 14.09.2017 Email to TP: sent out letter and survey. | Premier Farnell | E2E Testing | TP Coms Except | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-19
2.2 | EU | AVNET LTD | AVNETUK | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVNET | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | Inovis |  | Mark.Mcgill@xyz.com |  |  | Ready to start E2E testing |  | TP | E2E Testing | TP Coms Except | 31/07/2017 | 31/07/2017 | 2017-07-08 | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 06/09/2017 |  |  |  |  | 2018-02-19
2.2 | EU | AVNET LTD | AVNETUK | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVNET | PORDCHG | ORDCHG | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | Inovis |  | Mark.Mcgill@xyz.com |  |  | Ready to start E2E testing |  | TP | E2E Testing | TP Coms Except | 18/10/2017 | 18/10/2017 | 18/10/2017 |  |  | PF_O_E_ORDCHG_D97A_FAR | Primary | E_ORDCHG_D97A_FAR | 13/12/2017 | 17/11/2017 |  |  |  |  | 2018-02-19
2.2 | EU | AVNET LTD | AVNETUK | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVNET | PINVOICE | INVOIC | IB | MQ | EDIFACT | D97A |  | VAN | Inovis |  | Mark.Mcgill@xyz.com |  |  | Ready to start E2E testing |  | TP | E2E Testing | TP Coms Except | 2017-05-10 | 2017-05-10 | 17/10/2017 |  |  | PF_I_E_INVOIC_D97A_FP_GENERIC | Primary | E_INVOIC_D97A_FPX | 11/12/2017 | 31/10/2017 |  |  |  |  | 2018-02-19
2.2 | EU | AVNET LTD | AVNETUK | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVNET | DESADV | DESADV | IB | MQ | EDIFACT | D97A |  | VAN | Inovis |  | Mark.Mcgill@xyz.com |  |  | Ready to start E2E testing |  | TP | E2E Testing | TP Coms Except | 2017-03-10 | 2017-03-10 | 2017-06-10 |  |  | PF_I_E_DESADV_D97A_FA3 | Primary | E_DESADV_D97A_FA3 | 14/12/2017 | 13/10/2017 |  |  |  |  | 2018-02-19
2.2 | EU | AVNET LTD | AVNETUK | 1 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVNET-(ST) | POINTOS | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/ST | VAN | Inovis |  | Mark.Mcgill@xyz.com |  |  | Ready to start E2E testing |  | TP | E2E Testing | TP Coms Except | 19/9/2017 | 19/9/2017 | 29/9/2017 |  |  | PF_O_E_SLSRPT_D97A_FAB | Primary | E_SLSRPT_D97A_FAB | 07/12/2017 | 05/10/2017 |  |  |  |  | 2018-02-19
2.1 | EU | AVX LTD | 5013546003650 | 1 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVX-LTD | DESADV | DESADV | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | jayne.wilson@tp8.com |  | start testing 19.02.18 | Ready to start E2E testing | 09.02 Email from TP - Hi Farnell team When we get a chance to test , I am off for a few days next week so we will try to get testing complete in the week starting 19th Feb Thanks & Regards Jayne 08.02.2018 ; Followup sent to TP on Inbound files 05.02.2018 Email from TP - Hi Farnell team Yes I received your files AS you can imagine, we have setups & tests to do, we will try to get these done as soon as we can 02.02. sent files to TP as attachment and via VAN, TP to confirm 31.01.2018 TP confirmed ready to test 31.01.2018: Email to TP - Hello Jayne, An initial email was sent to AVX on 09/07/2017 informing about Premier Farnerll's change in EDI ID's (Test : 5051259000285 Prod: 5051259000773). Richard ( copied in email) had confirmed back that you had notified your VAN provider GXS about the same. Kindly let us know if you are ready to receive test files from Premier Farnell's new test EDI ID 5051259000285 . 30.01.2018: Email from TP - Corinna Please give us more details of what this means ? Are you changing your sender/recipient id ? Are there any mapping changes ? 30.01.2018 Email to TP: sent out letter for E2E testing. 10.10.2017 Email from TP: the connection has been setup and confirmed by our provider. 09.10.2017 - Email to TP 4th Remainder sent 29.09.2017 Email to TP: sent request again letter and survey 28.09.2017 Email from TP: What exactly do you need from us please ? 28.09.2017 Email to TP: 3rd Reminder 22.09.2017 Email from TP: I am off on hols at the minute, I will reply when I return next week 21.09.2017 Email to TP sent out 2nd reminder 18.09.2017 Email to TP sent out 1st reminder 14.09.2017 Email to TP: sent out letter and survey. | TP | E2E Testing | E2E Test Slot Agreed | 2017-03-10 | 2017-03-10 | 2017-06-10 |  |  | PF_I_E_DESADV_D97A_FA3 | Primary | E_DESADV_D97A_FA3 | 14/12/2017 | 13/10/2017 |  |  |  |  | 2018-02-12
2.1 | EU | AVX LTD | 5013546003650 | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVX-LTD | PINVOICE | INVOIC | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | jayne.wilson@tp8.com |  | start testing 19.02.18 | Ready to start E2E testing |  | TP | E2E Testing | E2E Test Slot Agreed | 2017-05-10 | 2017-05-10 | 17/10/2017 |  |  | PF_I_E_INVOIC_D97A_FP_GENERIC | Primary | E_INVOIC_D97A_FPE | 11/12/2017 | 31/10/2017 |  |  |  |  | 2018-02-12
2.1 | EU | AVX LTD | 5013546003650 | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVX-LTD | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  | VAN | GXS |  | jayne.wilson@tp8.com |  | start testing 19.02.18 | Ready to start E2E testing |  | TP | E2E Testing | E2E Test Slot Agreed | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-12
2.1 | EU | AVX LTD | 5013546003650 | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVX-LTD | PORDER | ORDERS | OB | MQ | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | jayne.wilson@tp8.com |  | start testing 19.02.18 | Ready to start E2E testing |  | TP | E2E Testing | E2E Test Slot Agreed | 31/07/2017 | 31/07/2017 | 2017-07-08 | 2017-07-08 | 2017-10-08 | PF_O_E_ORDERS_D97A_FA9 | Primary | E_ORDERS_D97A_FA9 | 05/12/2017 | 06/09/2017 |  |  |  |  | 2018-02-12
2.1 | EU | AVX LTD | 5013546003650 | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVX-LTD | INVENTORY | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | jayne.wilson@tp8.com |  | start testing 19.02.18 | Ready to start E2E testing |  | TP | E2E Testing | E2E Test Slot Agreed | 31/08/2017 | 2017-05-09 | 2017-07-09 |  |  | PF_O_E_INVRPT_D97A_FA2 | Primary | E_INVRPT_D97A_FA2 | 08/12/2017 | 14/09/2017 |  |  |  |  | 2018-02-12
2.1 | EU | AVX LTD | 5013546003650 | 0 | ZZ | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | AVX-LTD | POINTOS | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR | VAN | GXS |  | jayne.wilson@tp8.com |  | start testing 19.02.18 | Ready to start E2E testing |  | TP | E2E Testing | E2E Test Slot Agreed | 2017-01-09 | 2017-06-09 | 14/9/2017 |  |  | PF_O_E_SLSRPT_D97A_FAR | Primary | E_SLSRPT_D97A_FAR | 08/12/2017 | 28/09/2017 |  |  |  |  | 2018-02-12
2.1 | EU | BAHCO TOOLS LTD | 5013546140685 | 1 | 14 | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 | 14 | BAHCO | PORDERACK | ORDRSP | IB | MQ | EDIFACT | D97A |  |  | OpusCapita |  | jayne.wilson@tp8.com |  | reminder 15.02.2018 | Ready to start E2E testing | 13.02 4th Reminder sent 09.02 Email from TP - Hello Kusum,I’m sorry, but I still have not received a response from SNA. 09.02.2018 3rd Followup sent 07.02 2nd followup sent about returning ORDRSP 02.02. followup to TP about ORDRSP 30.1.2018 Email from TP : Hello Kusum, We have received the file. I will forward it to SNA Europe (BAHCO TOOLS) and get back to you when we are ready to send ORDRSP in return.30.01.2018: Sent test orders, TP yet to confirm receipt 24.01.2018: E2E testing email sent 25.10.2017: Email from TP - Hi Kusum, In that case it is Okay to use the same FTP account edi0444 for Premier Farnell as well. Do you want to receive the ORDRSP to this account? If yes, the folder where we will put the ORDRSP messages is called “fromeditorg” and you must retrieve files from there. Please note that in case of Electrocomponents (ID 5060214370004 /ZZ) we only receive ORDERS to this account but ORDRSP are sent by us to another FTP - ftp.gts.globalec.com. 25.10.2017: Email to TP - Hello Eriks, Yes we would like to receive the ORDRSP messages to same FTP account. Thanks for confirming, I will be sharing the below details with our technical team. 25.10.2017: Email to TP : Hi Eriks, The EDI code 5013546140685 / 14 is linked to the FTP account edi0444 and is used by other Sterling customers, such as Electrocomponents (ID 5060214370004 /ZZ). Once Premier Farnell goes live on the IBM network, we would submit data for BAHCO to the same FTP account and the X.400 connection will become obsolete. If that is not possible, please provide your X.400 address for configuration on our end. In return you will receive the new Premier Farnell X.400 address. I must stress that we would prefer to use the existing FTP connection. 24.10.2017: Email from TP : Hello Kusum,Yes, the EDI code belongs to BAHCO TOOLS LTD (SNA Europe).Currently we receive from and send files to Premier Farnell using x400 connection. So is this going to be anged to FTP instead? The FTP account edi0444 is registered to Rs Components. Do you also send their files to this account? 24.10.2017: Email to TP - Hello Eriks,Can you please confirm that your EDI code is 5013546140685 / 14.We have this ID configured for an FTP connection to Remote IP address: ftp.itella.se / FTP ID: edi0444. Could we use that connection to send Premier Farnell data in the future ? 24.10.2017: Email to TP : Hello Eriks,Thank you for confirming. For now only EDI codes would be changing for Premier Farnell. We will be able to start testing in approximately eight weeks time. We will keep you posted when we are closer to the change. 24.10.2017: Email from TP Hello,We, OpusCapita, are EDI service provider for SNA Europe (BAHCO TOOLS LTD). I will be the contac person for this change on our side.Regarding the information below. Yes, the EDI code, Message Type, Message Format, and version are correct. Not sure about the Comm Type and Provider. The communication between OpusCapita and Farnell is x400 connection. Please let me know if you have more questions on the current setup and when and how you want to perform a test of the new setup. Are there going to be any changes to format/connection type or is it just the EDI codes that will be new?23.10.2017: Email to TP Folowup email sent 17.10.2017: Email to TP, TP survey introduction email sent to new TP contact | TP | E2E Testing | Waiting on TP Coms2 | 27/10/2017 | 27/10/2017 | 13/12/2017 |  |  | PF_I_E_ORDRSP_D97A_FA2 | Primary | E_ORDRSP_D97A_FA2 | 13/12/2017 | 15/12/2017 |  |  |  |  | 2018-02-12
Legend (color): |  | pending validation
issues
Note on C141: ADMINIBM: EPCOS (Siemens Business System)
Note on C142: ADMINIBM: EPCOS (Siemens Business System)
Note on C143: ADMINIBM: EPCOS (Siemens Business System)
Note on C144: ADMINIBM: EPCOS (Siemens Business System)
Note on C145: ADMINIBM: EPCOS (Siemens Business System)
Note on C146: ADMINIBM: EPCOS (Siemens Business System)

## Duplicates
Release Lvl | Region | TP Company Name | TP's EDI code | Helper | TP Qualifier | PF's new EDI Codes | PF's new EDI Qualifier | PF 's old EDI Codes | PF's old EDI Qualifier | REIMS /TP a/c number | REIMS Interchange | Message Type | Direction To/From Client | SFTP / MQ Protocol | Message Format | Version | Envelope Variant | Comms Type | TP's Provider | X.400 address (if applicable) | Contact Name/Email address | Telephone | CDS Notes | CDS Info | Comments | Action's Owner | Relationship Status | TP Overall Status | Specs Received (Date) | Test Data Received (Date) | MRS created (Date) | MRS Signed off (Date) | Maps approved for System Test (Date) | IBM Mapname | Map Type | REIMS Base Map To Use | Map Loaded (Date) | TP Setup (Date) | System Test (Date) | System Test Signed off (Date) | End to End Test Planned (Date) | End to End Test Signed off (Date) | Go Live Planned (Date) | Moved To production (Date) | Go Live (Date)
3 | EU | FAIRCHILD SEMICONDUCTOR LTD | FAIRCHILD | 1 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | FAIRCHILD | POINTOS | SLSRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR | VAN | Inovis |  | denise.hunt@fairchildsemi.com |  |  |  | Tom.Kennedy@onsemi.com | CDS | Not started | Not started | 19/9/2017 | 19/9/2017 | 29/9/2017 |  |  | PF_O_E_SLSRPT_D97A_FA_GENERIC | Primary | E_SLSRPT_D97A_FA4 | 03/10/2017 | 05/10/2017
3 | AU | TEXAS INSTRUMENTS LTD | GBTXI.TXI002 | 1 |  | Test : 5051259000292 Prod: 5051259000780 |  | 5013546005195 |  | TEXAS-SG | INVENTORYA | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/TI | VAN - GXS |  |  | jason.hsieh@ti.com |  |  |  |  | CDS | Not started | Not started | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1A | 03/10/2017 | 05/10/2017
3 | SG | TEXAS INSTRUMENTS LTD | GBTXI.TXI002 | 0 |  | Test: 5051259000377 Prod:5051259000865 |  | 5013546005195 |  | TEXAS-SG | INVENTORYC | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/TI | VAN - GXS |  |  | jason.hsieh@ti.com |  |  |  |  | CDS | Not started | Not started | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1C | 03/10/2017 | 05/10/2017
3 | SG | TEXAS INSTRUMENTS LTD | GBTXI.TXI002 | 0 |  | Test: 5051259000377 Prod:5051259000865 |  | 5013546005195 |  | TEXAS-SG | INVENTORYI | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR | VAN - GXS |  |  | jason.hsieh@ti.com |  |  |  |  | CDS | Not started | Not started | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1I | 03/10/2017 | 05/10/2017
3 | SG | TEXAS INSTRUMENTS LTD | GBTXI.TXI002 | 0 |  | Test: 5051259000377 Prod:5051259000865 |  | 5013546005195 |  | TEXAS-SG | INVENTORYS | INVRPT | OB | SFTP | EDIFACT | D97A | INS/UNOA/FAR/TI | VAN - GXS |  |  | jason.hsieh@ti.com |  |  |  |  | CDS | Not started | Not started | 15/9/2017 | 15/9/2017 | 23/9/2017 |  |  | PF_O_E_INVRPT_D97A_F1_GENERIC | Primary | E_INVRPT_D97A_F1S | 03/10/2017 | 05/10/2017
2 | EU | HIROSE ELECTRONIC EUROPE B V | 5013546288646 | 1 |  | Test : 5051259000285 Prod: 5051259000773 |  | 5013546005195 |  | HIROSE | PINVOICE | INVOIC | IB | MQ | EDIFACT | D97A |  | VAN | GXS | [5 empty] | 12.09.2017 Emailto Client: ask for new contact details (old contact details: s.martindale@hiroseeurope.eu) 7.9.2017 1st letter to the TP/ bounced back | Premier Farnell | Discovery | Awaiting Contact Details | 2017-05-10 | 2017-05-10 | 17/10/2017 |  |  | PF_I_E_INVOIC_D97A_FP_GENERIC | Primary | E_INVOIC_D97A_FPE | 31/10/2017 | 31/10/2017

## OldDashboard
Sum of Helper
Release Lvl | TP Overall Status | Total | Overall TP Status | Description
1 | De-scoped | 2 | De-Scoped | Removed from the scope of the project
| Live | 10 | Await Contact Details | IBM Awaiting contact details from PF
| TP Coms Except | 1 | Not Started | IBM have not contacted the TP yet
1 Total |  | 13 | Waiting on TP Coms1 | 1st Contact Letter sent by IBM
2 | Await Contact Details | 9 | Waiting on TP Coms2 | 2nd Contact Letter sent by IBM
| BizTalk | 5 | Waiting on TP Coms3 | 3rd Contact Letter sent by IBM
| De-scoped | 6 | TP Coms Except | Coms Exception, PF to follow up with TP, no response to IBM
| E2E Testing | 1 | On Hold | TP on hold for some reason - See comments
| On hold | 1 | Discovery | IBM in discussions with TP to understand requirements
| System Testing | 61 | TP Setup | IBM have set up the TP in the Test System
| TP Coms Except | 14 | System Testing | PF/IBM testing
| TP Setup | 28 | E2E Testing | TP has confirmed readiness to test and window has been confirmed
| Waiting on TP Coms1 | 1 | Production Readiness | Testing Completed Ready to Migrate
| Waiting on TP Coms3 | 2 | E2E Test Failed | Test Failed Change Required
2 Total |  | 128 | Migration Booked | Migration Data Booked with TP and PF
3 | BizTalk | 1 | Live | Migration Complete
| De-scoped | 5 | Non-EDI Process | PF will (temporarily) move to Non-EDI process
| Not started | 21
| TP Setup | 1
3 Total |  | 28
4 | Not started | 2
4 Total |  | 2
Legend (color): | (blank)
Legend (color): Total
(blank) | (blank)
(blank) Total
Grand Total |  | 171